## 📅 Weekly Overview
IT3030 PAF 2026 — Smart Campus Hub ¦ Weekly Task Tracker
Submission Deadline: 27 April 2026 ¦ Viva: from 11 April 2026
Week | Dates | Focus | Member 1 (Facilities + Analytics) | Member 2 (Booking + Conflict) | Member 3 (Tickets + SLA) | Member 4 (Auth + Notifications)
Week 1 | 24–30 Mar | 🏗️ Foundation | ✅ Spring Boot project setup ✅ resources table + entity ✅ Basic GET /resources stub | ✅ bookings table + entity ✅ Repo + service layer setup ✅ Review DB schema with team | ✅ tickets, images, comments tables ✅ Entity classes setup ✅ Review DB schema with team | 🔥 OAuth 2.0 Google login 🔥 JWT token config 🔥 USER / ADMIN / TECHNICIAN roles 🔥 SecurityConfig — secure all endpoints
Week 2 | 31 Mar–6 Apr | ⚙️ Core CRUD | ✅ POST /resources ✅ PUT /resources/{id} ✅ DELETE /resources/{id} ✅ Status: ACTIVE/OUT_OF_SERVICE | ✅ POST /bookings (PENDING state) ✅ GET /bookings/my ✅ Basic validation (dates, capacity) | ✅ POST /tickets ✅ GET /tickets ✅ PUT /tickets/{id}/status (OPEN→IN_PROGRESS) | ✅ GET /notifications (empty list OK) ✅ users table populated on OAuth login ✅ Role-based endpoint guards
Week 3 | 7–13 Apr | 🧠 Core Logic | ✅ GET /resources/search (type, capacity, location filters) ✅ resource_availability table ✅ GET /resources/{id}/availability | 🔥 Time-overlap conflict detection algorithm ✅ PUT /bookings/{id}/approve ✅ PUT /bookings/{id}/reject (with reason) | ✅ POST /tickets/{id}/images (upload, validate type+size) 🔥 Technician assignment: PUT /tickets/{id}/assign ✅ RESOLVED → CLOSED workflow | ✅ Notification triggers: booking approved/rejected ✅ NotificationService.notifyUser() method ready ✅ PUT /notifications/read
Week 4 | 14–20 Apr | 🔗 Integration | 📊 Admin analytics endpoints: GET /admin/analytics/top-resources GET /admin/analytics/today GET /admin/analytics/peak-hours (JPA aggregation on bookings table) | ✅ PUT /bookings/{id}/cancel ✅ GET /bookings/all (Admin, with filters) 🔥 Auto-expire cron job (PENDING → EXPIRED after 24h) | ✅ POST /tickets/{id}/comment 🔥 SLA timer: time-to-first-response 🔥 SLA timer: time-to-resolution → Call notificationService on new comment | ✅ Ticket status change notifications ✅ New comment notifications (triggered by M3) ✅ GET /audit (admin only) ✅ Audit log on key actions
Week 5 | 21–23 Apr | 🎨 Frontend | 🖥️ Resource list page (filterable) 🖥️ Add/Edit resource form 🖥️ Availability calendar component 🖥️ Admin dashboard cards (analytics) | 🖥️ Booking request form 🖥️ My Bookings page 🖥️ Admin approval UI (approve/reject buttons) | 🖥️ Create ticket page 🖥️ Ticket list + detail view 🖥️ Comment section 🖥️ Status update UI + SLA display | 🖥️ OAuth login page 🖥️ Protected route guards 🖥️ Notification bell + panel 🖥️ Admin audit log viewer
Week 6 | 24–25 Apr | 🧪 Test + Polish | ✅ Postman collection for own endpoints ✅ Edge case testing (invalid filters) ✅ UI polish + error messages | ✅ Unit test conflict algorithm ✅ Test cron job behavior ✅ UI polish + loading states | ✅ Image upload edge cases ✅ SLA accuracy check ✅ UI polish + comment ownership rules | ✅ OAuth flow end-to-end test ✅ Role-switching test (USER vs ADMIN) ✅ Notification delivery verification
Week 7 | 26–27 Apr | 📄 Submit | 📝 Write own section in report 📝 List endpoints + diagrams 📸 Screenshots of resource + analytics UI | 📝 Write own section in report 📝 Explain conflict algorithm 📸 Screenshots of booking flow | 📝 Write own section in report 📝 Explain SLA logic 📸 Screenshots of ticket lifecycle | 📝 Write own section in report 📝 Auth + audit section 📸 OAuth login + notification screenshots

## 👤 Member 1
Member 1 — Facilities + Availability + Analytics
📦 Tables Owned: resources, resource_availability
REST API Endpoints
Method | Endpoint | Description | Role | Status Code
POST | /resources | Create a new resource | Admin | 201 Created
GET | /resources | List all resources (paginated) | All | 200 OK
PUT | /resources/{id} | Update resource details | Admin | 200 OK
DELETE | /resources/{id} | Delete a resource | Admin | 204 No Content
GET | /resources/search | Search by type, capacity, location | All | 200 OK
GET | /resources/{id}/availability | Get availability windows | All | 200 OK
GET | /admin/analytics/top-resources | Top 5 booked resources | Admin | 200 OK
GET | /admin/analytics/today | Total bookings today | Admin | 200 OK
GET | /admin/analytics/peak-hours | Peak booking hours | Admin | 200 OK
📋 Task Breakdown by Week
Week | Task / Deliverable
Week 1 | Spring Boot project setup + DB connection
Week 1 | resources + resource_availability entities
Week 2 | POST /resources — full CRUD with validation
Week 2 | PUT /resources/{id} — update + status change
Week 2 | DELETE /resources/{id}
Week 2 | GET /resources — list with pagination
Week 3 | GET /resources/search — filters: type, capacity, location
Week 3 | resource_availability table + availability window logic
Week 3 | GET /resources/{id}/availability — calendar generation
Week 4 | JPA aggregation queries on bookings table
Week 4 | Analytics endpoints: top-resources, today, peak-hours
Week 5 | React: Resource list page with search + filter UI
Week 5 | React: Add/Edit resource form (admin only)
Week 5 | React: Availability calendar component
Week 5 | React: Admin dashboard analytics cards
Week 6 | Postman collection for all 9 endpoints
Week 6 | Edge case testing + UI polish
Week 7 | Write report section + screenshots

## 👤 Member 2
Member 2 — Booking Workflow + Conflict Engine + Auto Expire
Angeli Tharushika IT23144408
📦 Tables Owned: bookings
REST API Endpoints
Method | Endpoint | Description | Role | Status Code
POST | /bookings | Create a booking request | User | 201 Created
GET | /bookings/my | Get current user's bookings | User | 200 OK
GET | /bookings/all | Get all bookings (with filters) | Admin | 200 OK
PUT | /bookings/{id}/approve | Approve a booking | Admin | 200 OK
PUT | /bookings/{id}/reject | Reject with reason | Admin | 200 OK
PUT | /bookings/{id}/cancel | Cancel an approved booking | User/Admin | 200 OK
📋 Task Breakdown by Week
Week | Task / Deliverable
Week 1 | bookings entity + repository setup
Week 1 | Review + agree DB schema (foreign keys)
Week 2 | POST /bookings — create with PENDING state
Week 2 | GET /bookings/my — user-scoped query
Week 2 | Basic validation: past dates, missing fields
Week 3 | 🔥 Time-overlap conflict detection algorithm
Week 3 | PUT /bookings/{id}/approve — PENDING → APPROVED
Week 3 | PUT /bookings/{id}/reject — with rejection reason
Week 4 | PUT /bookings/{id}/cancel — APPROVED → CANCELLED
Week 4 | GET /bookings/all — admin view with status filters
Week 4 | 🔥 Cron job: auto-expire PENDING bookings after 24h
Week 5 | React: Booking request form
Week 5 | React: My Bookings page (timeline view)
Week 5 | React: Admin approval UI (approve/reject buttons)
Week 6 | Unit test: conflict detection edge cases
Week 6 | Test cron job + UI polish
Week 7 | Write report section + conflict algorithm diagram

## 👤 Member 3
Member 3 — Incident Tickets + SLA + Comments + Images
📦 Tables Owned: tickets, ticket_images, comments
REST API Endpoints
Method | Endpoint | Description | Role | Status Code
POST | /tickets | Create incident ticket | User | 201 Created
GET | /tickets | List tickets (role-filtered) | All | 200 OK
PUT | /tickets/{id}/status | Update ticket status | Admin/Tech | 200 OK
PUT | /tickets/{id}/assign | Assign technician | Admin | 200 OK
POST | /tickets/{id}/comment | Add comment to ticket | All | 201 Created
POST | /tickets/{id}/images | Upload up to 3 images | User | 201 Created
📋 Task Breakdown by Week
Week | Task / Deliverable
Week 1 | tickets, ticket_images, comments entities
Week 1 | Review + agree DB schema with team
Week 2 | POST /tickets — create with OPEN state
Week 2 | GET /tickets — list with role-based filtering
Week 2 | PUT /tickets/{id}/status — OPEN→IN_PROGRESS
Week 3 | POST /tickets/{id}/images — upload, type+size validation
Week 3 | PUT /tickets/{id}/assign — technician assignment
Week 3 | RESOLVED → CLOSED workflow + REJECTED with reason
Week 4 | POST /tickets/{id}/comment — with ownership rules
Week 4 | 🔥 SLA: time-to-first-response tracking
Week 4 | 🔥 SLA: time-to-resolution tracking
Week 4 | Trigger notificationService.notifyTicketOwner() on comment
Week 5 | React: Create ticket page
Week 5 | React: Ticket list + detail view
Week 5 | React: Comment section + edit/delete (own)
Week 5 | React: Status update UI + SLA timer display
Week 6 | Image upload edge cases + SLA accuracy check
Week 7 | Write report section + SLA logic diagram

## 👤 Member 4
Member 4 — Authentication + Roles + Notifications + Audit Logs
📦 Tables Owned: users, notifications, audit_logs
REST API Endpoints
Method | Endpoint | Description | Role | Status Code
GET | /oauth2/callback | OAuth 2.0 Google login callback | Public | 302 Redirect
GET | /notifications | Get user notifications | User | 200 OK
PUT | /notifications/read | Mark all as read | User | 200 OK
PUT | /notifications/{id}/read | Mark single as read | User | 200 OK
GET | /audit | Admin audit log viewer | Admin | 200 OK
GET | /users/me | Get current user profile + role | User | 200 OK
📋 Task Breakdown by Week
Week | Task / Deliverable
Week 1 | 🔥 OAuth 2.0 Google Sign-in integration
Week 1 | 🔥 JWT token generation + validation
Week 1 | 🔥 Roles: USER, ADMIN, TECHNICIAN
Week 1 | 🔥 SecurityConfig — secure all endpoints by role
Week 2 | users table auto-populated on first OAuth login
Week 2 | GET /users/me — return profile + role
Week 2 | Role-based guards on all existing endpoints
Week 3 | NotificationService — notifyUser() method
Week 3 | Notification triggers: booking approved/rejected
Week 3 | GET /notifications + PUT /notifications/read
Week 4 | Ticket status change notification triggers
Week 4 | New comment notification (called by Member 3)
Week 4 | AuditLog entity + AuditService
Week 4 | GET /audit — admin-only log viewer
Week 5 | React: OAuth login page
Week 5 | React: Role-based protected routes
Week 5 | React: Notification bell icon + dropdown panel
Week 5 | React: Admin audit log viewer page
Week 6 | OAuth full flow end-to-end test
Week 6 | Role-switching test (USER vs ADMIN views)
Week 7 | Write report section + auth flow diagram

## 🗄️ DB Schema
Database Schema — Key Tables & Foreign Keys
Table | Column | Type / Constraint | Owner
users | id | BIGINT PK AUTO | M4
| oauth_id | VARCHAR UNIQUE
| name | VARCHAR
| email | VARCHAR UNIQUE
| role | ENUM: USER/ADMIN/TECHNICIAN
| created_at | TIMESTAMP
resources | id | BIGINT PK AUTO | M1
| name | VARCHAR
| type | ENUM: HALL/LAB/ROOM/EQUIPMENT
| capacity | INT
| location | VARCHAR
| status | ENUM: ACTIVE/OUT_OF_SERVICE
| created_at | TIMESTAMP
resource_availability | id | BIGINT PK AUTO | M1
| resource_id | BIGINT FK → resources.id
| day_of_week | ENUM: MON-SUN
| start_time | TIME
| end_time | TIME
bookings | id | BIGINT PK AUTO | M2
| user_id | BIGINT FK → users.id
| resource_id | BIGINT FK → resources.id
| start_time | TIMESTAMP
| end_time | TIMESTAMP
| purpose | VARCHAR
| attendees | INT
| status | ENUM: PENDING/APPROVED/REJECTED/CANCELLED/EXPIRED
| rejection_reason | VARCHAR NULL
| created_at | TIMESTAMP
tickets | id | BIGINT PK AUTO | M3
| user_id | BIGINT FK → users.id
| resource_id | BIGINT FK → resources.id
| category | VARCHAR
| description | TEXT
| priority | ENUM: LOW/MEDIUM/HIGH/CRITICAL
| status | ENUM: OPEN/IN_PROGRESS/RESOLVED/CLOSED/REJECTED
| assigned_to | BIGINT FK → users.id NULL
| first_response_at | TIMESTAMP NULL
| resolved_at | TIMESTAMP NULL
| created_at | TIMESTAMP
ticket_images | id | BIGINT PK AUTO | M3
| ticket_id | BIGINT FK → tickets.id
| file_path | VARCHAR
| file_type | VARCHAR
| file_size | BIGINT
| uploaded_at | TIMESTAMP
comments | id | BIGINT PK AUTO | M3
| ticket_id | BIGINT FK → tickets.id
| user_id | BIGINT FK → users.id
| content | TEXT
| created_at | TIMESTAMP
| updated_at | TIMESTAMP NULL
notifications | id | BIGINT PK AUTO | M4
| user_id | BIGINT FK → users.id
| type | ENUM: BOOKING_APPROVED/BOOKING_REJECTED/TICKET_UPDATED/NEW_COMMENT
| message | VARCHAR
| is_read | BOOLEAN DEFAULT false
| ref_id | BIGINT
| ref_type | VARCHAR
| created_at | TIMESTAMP
audit_logs | id | BIGINT PK AUTO | M4
| actor_id | BIGINT FK → users.id
| action | VARCHAR
| entity_type | VARCHAR
| entity_id | BIGINT
| detail | TEXT NULL
| performed_at | TIMESTAMP